## Instructions and Guidance
Delivery Plan Template
-This Delivery Plan Template aims to provide a standardised approach to the delivery of neighbourhood-level adaptation infrastructure projects. - The template is suitable for short-term (up to 9 months), specific and local interventions on new or existing infrastructure. -Example projects that the user may want to use the template for include: drainage systems, urban park adaptation measures, and permeable pavements. -The five key stages (expanded in the following tab) that can be tailored for a specific intervention are outlined below:
Kick off and project management | Following award of the contract, the process to achieve an effective kick-off, a clear project plan and the standard reporting/programme management practices to the client.
Planning and pre-construction | The key steps required before construction can commence. These will include the key steps to design the intervention, stakeholder engagement (both from a community and permitting perspective), through to finalisation of materials and resources.
Construction Phase | The key steps to deliver the intervention or initiative. Additional and tailored steps should be added for the specific initiative but the outlined steps can be used as guidance.
Testing and inspection | Tailoring and adjustments to confirm safety and quality of final structure.
Project completion and post-construction | The process to finalise the project; including any required inspections and documentation, engagement to handover the project to the community, and ongoing monitoring and evaluation.

## Delivery Plan Template
Key
Duration of activity
Finalisation of activity / deliverable
| Month 1 |  |  |  | Month 2 |  |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  |  | Month 6
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
Kick off and project management
Contact finalisation, project plan and kick off meeting | bar: Month 1 W1 to Month 1 W2
Initial budget, estimation of costs and timelines. Budget planning should then extend through the following stages (until post-construction). | bar: Month 1 W1 to Month 1 W2; Month 2 W5; Month 2 W7; Month 3 W10; Month 3 W12; Month 4 W14; Month 4 W16; Month 5 W18; Month 5 W20; Month 6 W23
Monthly project management meetings with client | bar: Month 2 W5; Month 3 W10; Month 4 W14; Month 5 W18; Month 6 W23
Planning and pre-construction
Design Development (initial Exeuction Plan) Create plans for infrastructure For example, drainage systems, urban park adaptation measures, permeable pavements
Stakeholder Engagement Gather input from residents and local organizations.
Community Assessment Analyse local climate vulnerabilities and needs
Permitting Secure necessary permits from local authorities Please note that as these processes are likely to require a series of municipal and public servcies approval processes, a buffer should be introduced to accomodate both that: 1. Approval may not be immediately received. 2. Blueprints may have to be updated or resubmitted following feedback.
Initial Site Preparation (Logistics and Administration) Key coordination activities to ensure appropriate management of local space with local managers and community, and any mitigation activity or plans. For example, if the construction requires part of a school to close, plans to cordon off areas, relocate students or playing fields, paths of travel and potential impact on local community measured
Final bill of quantities Prices and quantities of all specified materials chosen for the intervention and needed for the construction are identified.
Final Execution Plan Clear timelines for delivery project, including clearly listed construction phase steps
Material Procurement Source sustainable and climate-resilient materials
Resource Allocation Assign project teams and equipment
Construction Phase
Site Preparation Clear and prepare areas for construction for construction (any remaining architecutral and engineering activities). For example, land leveling or changes or removal of existing infrastructure
Construction Step 1 (e.g structure)
Construction Step 2 (e.g. main activity)
Construction Step 3 (e.g design feastures, flood resistance, etc)
Construction Step 4 (final steps, e.g. planting trees and native vegetation around system)
Testing and inspection
Quality Control Conduct inspections of installations, ensuring compliance with design, objective and relevant standards Please note that Quality Control will be present throughout the Construction Phase and should be reflected accoridngly
Adjustments and tweaks Make modifications based on feedback or testing results
Project completion and post-construction
Final Inspection Ensure all elements are operational and meet standards
Documentation Complete project records, including maintenance guidelines
Community Engagement Educate residents on the new systems and their maintenance
Community Handover Transfer maintenance responsibilities to local authorities or community groups
Monitoring, Evaluation and Learning. Establish protocols to assess the effectiveness of adaptation measures, and any learnings from the project.

## Tabelle1 (hidden)
Organizations | Platform-Projects
IDB Cities Network |  | Legend - Next Steps
Adaptation Fund |  | Further research / Consultant
Africa Climate Change Fund |  | Check with Country teams
African Center for Cities |  | Low potential
Banco de Desarrollo de América del Norte (BDAN) |  | High potential
Banco Interamericano de Desarrollo (BID)
Banobras (Programa FAIS)
BBC Media Action
Bonos Verdes - BMV
C40
Cities Alliance
City Climate Finance Gap Fund
Corporación Andina de Fomento (CAF)
Deutsche Welle
DWS
Environment and Rural Development in Latin America (GADeR-ALC)
European Union
Fab City Yucatán - Centro de innovación urbana
Fondo Chile-México- AMEXCID- AGCID
Fondo de Cambio Climático
Fondo Nacional de Infraestructura - FONADIN
Fondo para el Medio Ambiente Mundial (FMAM)
Fundación Chalchi A.C.
Fundación del Empresariado Yucateco A.C.
Global Center on Adaptation
Global Covenant of Mayors for Climate & Energy (GCoM)
Global Environment Facility (GEF)
Global Facility for Disaster Reduction and Recovery (GFDRR)
Global Green Growth Institute (GGGI)
Good Governance Africa (GGA)
Google (sustainability.google)
Governance and Democracy in Latin America (Red-LAC)
Green Climate Fund (GCF)
ICLEI – Local Governments for Sustainability
ICLEI
IKI Small Grants
International Climate Initiative (IKI)
International Development Finance Club (IDFC)
International Institute for Environment and Development (IIED)
International Institute for Sustainable Development (IISD)
Kanan Kab
KfW Development Bank
Least Developed Countries Fund (LDCF)
Merida Universities (various)
Morgenstadt: City Insights
National Treasury South Africa
Oox Beh
Private Insurance companies (various)
Resilient Cities Network
Resilient Cities
Rural Development Africa (SNRD)
Semillas del Futuro A.C.
SlumDwellers International
South African Local Government Association (SALGA)
Special Climate Change Fund (SCCF)
UK PACT Country Programmes
UN-Habitat Global
United Cities and Local Governments (UCLG)
USAID
World Bank
Global IBA (funds for cities)

## Tabelle2 (hidden)
Zeilenbeschriftungen
High
Implementation - Financing
Banobras (Programa FAIS)
National Treasury South Africa
UN-Habitat Global
Fondo de Cambio Climático de la Península de Yucatán (FCCPY) - Quintana Roo, Campeche y Yucatán / Yucatán Peninsula Climate Change Fund (FCCPY) -
Implementation - Technical Support
Fab City Yucatán - Centro de innovación urbana
Fundación Chalchi A.C.
Fundación del Empresariado Yucateco A.C.
Kanan Kab
Merida Universities (various)
Oox Beh
Semillas del Futuro A.C.
Network Association - Knowledge
IDB Cities Network
C40
Covenant of Mayors in Sub-Saharan Africa
Global Covenant of Mayors for Climate & Energy (GCoM)
ICLEI – Local Governments for Sustainability
South African Local Government Association (SALGA)
United Cities and Local Governments (UCLG)
Technical/Finance
City Climate Finance Gap Fund
International Climate Initiative (IKI) - IKI Small Grants
Cities Climate Finance Leadership Alliance
Political - Implementation
Ministry of Co-operative Governance and Traditional Affairs (CoGTA), South Africa
Low
Implementation - Financing
Adaptation Fund
Africa Climate Change Fund
Banco Interamericano de Desarrollo (BID)
Corporación Andina de Fomento (CAF)
Fondo Chile-México- AMEXCID- AGCID
Google (sustainability.google)
International Development Finance Club (IDFC)
KfW Development Bank
World Bank
Implementation - Technical Support
DWS (Department of Water and Sanitation / South Africa)
Network Association - Technical
Rural Development Africa (SNRD)
Governance and Democracy in Latin America (Red-LAC) - giz
Research Institution
International Institute for Environment and Development (IIED)
Morgenstadt: City Insights (Fraunhofer Morgen Initiative)
Technical/Finance
Banco de Desarrollo de América del Norte (BDAN)
UK PACT Country Programmes
Medium
Implementation - Financing
European Union
Fondo Nacional de Infraestructura - FONADIN
Green Climate Fund (GCF)
Private Insurance companies (various)
USAID
Implementation - Technical Support
Global Green Growth Institute (GGGI)
International Institute for Sustainable Development (IISD)
Media
BBC Media Action
Deutsche Welle
Network Association - Knowledge
Cities Alliance
Global Center on Adaptation
Regions4
Resilient Cities Network
SlumDwellers International
Network Association - Technical
Environment and Rural Development in Latin America (GADeR-ALC) - giz
Research Institution
African Center for Cities
Good Governance Africa (GGA)
Technical/Finance
Global Facility for Disaster Reduction and Recovery (GFDRR)
Global Environment Facility (GEF) / Fondo Mundial para el Medio Ambiente (FMAM)
Political - Implementation
"Ministry of Agrarian, Territorial and Urban Development, (Secretaría de Desarrollo Agrario, Territorial y Urbano, SEDATU)"
"Ministry of Environment and Natural Resources (Secretaría de Medio Ambiente y Recursos Naturales – SEMARNAT"
(Leer)
Implementation - Financing
FIDESUR
MIG
SANBI
DFFE
ACWA Platform
Network Association - Knowledge
KZN Climate Change Compact
TWG on Climate Change
Adaptation Network
NBI
SACN
IERM
RENAMET
CONACYT
EURESFO
European Urban Initiative (EUI)
weADAPT
Mexican Parc Association
Deutscher Städtetag
Political - Implementation
"Mexican Development Agency (Agencia Mexicana de Cooperación Internacional para el Desarrollo – AMEXCID)+"
Department of Forestry, Fisheries and the Environment (DFFE)
Gesamtergebnis